## Progress Log
Extractor Pod - Sprint Tracker
technext-edge repo - Casa Escondida Core & Edge Blueprint - updated as work happens, not after the fact
Date | Category | Item | Status | Notes | Ref (commit / doc)
2026-09-16 | Repo setup | Created TechNextSG/technext-edge (private repo) and linked Vercel project technext-edge-casa-bff - the Edge layer the Blueprint describes; nothing existed before this. | Done | No PoC pre-existed anywhere in the org for this - confirmed by searching casa-escondida-tools. | commit c9c0ec3.. (initial scaffold)
2026-09-16 | Extractor core | Built packages/extractor/: Trip schema (zod, per-field state), Manila-time relative-date resolver, house-norm defaults, verbatim-evidence enforcement, extract() pipeline. | Done | Trip schema and house-norm values are placeholders flagged inline - real ones need Phillip's frozen contract and Jett/Eloa respectively. | packages/extractor/src/
2026-09-16 | BFF + UI | Built apps/casa-bff/ (Hono, POST /v1/extract, GET /healthz) plus a test console at GET / for trying extraction without curl/Postman. | Done | Visual identity matches apps/estimate-tool in casa-escondida-tools on purpose. | apps/casa-bff/src/
2026-09-16 | Deploy debugging | Found and fixed 6 real deploy bugs in one session: monorepo subtree upload, Deployment Protection (SSO) blocking everything, Vercel framework auto-detect conflict, ESM/CJS mismatch, workspace-symlink resolution failing at runtime, git commit-author permission block. | Done | Documented in docs/01-team-guide.md section 8 (Known gotchas) so nobody re-debugs the same things. | README/team-guide commit history
2026-09-16 | Model bake-off prep | Added DeepSeek adapter (4th candidate) via the team's LiteLLM gateway; provider now selectable per env var (EXTRACTOR_PROVIDER) or per-request override (bring-your-own key from the test console). | Done | DeepSeek restricted to synthetic data only until the PII-masking-before-send question is resolved (Gate A). | packages/extractor/src/providerFromEnv.ts
2026-09-16 | Pipeline hardening | Retry on schema failure now hands the model its own bad output + the real zod error (was: identical blind retry). Transport failures (429/5xx) now return a distinct status from validation failures (was: both read as one generic 422). | Done | Found by actually running the eval harness against production, not by inspection. | packages/extractor/src/extract.ts
2026-09-16 | Eval harness | Built packages/extractor/eval/ (runner + researched synthetic dataset, 10 messages EN/VI/ZH) scoring against the Playbook's 5 thresholds. | Done | Synthetic data decides nothing per Playbook/ADR-005a - dry run only, proves the mechanism before Eloa's real 30 messages arrive. | packages/extractor/eval/
2026-09-16 | Eval dry run - Gemini | Ran the harness against Gemini 2.5 Flash. Found and fixed a scoring bug (house-norm default was miscounted as fabrication) and a pipeline bug (a 429 quota error was reported as a schema-validation failure). | Done | Both bugs fixed same day; see ADR-005a for detail. | docs/adr/ADR-005a-extractor-model.md
2026-09-16 | Eval dry run - DeepSeek | Ran the same harness against DeepSeek Flash. p95 latency 15.9s (over the 8s threshold); missed relative-date check-in extraction in 4/10 cases (tomorrow, this Friday, next Saturday in Chinese, in 5 days). | Done | Recorded as a lead to chase in the real bake-off, not a verdict - 10 synthetic messages decides nothing. | docs/adr/ADR-005a-extractor-model.md
2026-09-16 | Docs | Wrote docs/01-team-guide.md plus an HTML version with an EN/VI toggle (docs/team-guide.html) - prerequisites, running locally, the test console, deploying, env vars, eval harness, known gotchas. | Done | Two real bugs found by opening the HTML page in an actual browser: missing charset (VI text mojibake) and a CSS grid overflow from a long code line. | docs/01-team-guide.md, docs/team-guide.html
2026-09-16 | Security hygiene | Rotated GEMINI_API_KEY after the old value was pasted into chat multiple times. Flagged the DeepSeek gateway key (also pasted in chat) for Anthony to rotate. | Blocked | New Gemini key still hits 429 - Google's free-tier quota is per Cloud project, not per key, so rotating the key string alone did not reset it. | N/A - Vercel env vars, not committed

## Open Items
Open Items - Blocking the Real Bake-off (ADR-005b)
Nothing here is fixable in code - each needs a specific person
Item | Needs | Why it's blocked | Priority
Enable billing on the Gemini API key (or issue a paid-tier key) | Sky or Anthony (Google Cloud billing account owner) | Free tier: 20 req/day, per-Cloud-project (not per key - rotating the key string does not reset it). Cannot run 30 messages times multiple candidates at all on this tier. | High - blocks ADR-005b entirely
Rotate the DeepSeek LiteLLM gateway key | Anthony | Key was pasted into chat during today's testing. | High - security
Freeze Phillip's Trip schema (contracts/casa/estimate-api.v1.yaml) | Phillip | packages/extractor/src/schema.ts is currently a guess; the eval's ground truth will need rewriting once the real schema lands. | Medium
Confirm the real house-norm fields and default values | Jett / Eloa | houseNorms.ts currently guesses 4 fields and their defaults; wrong guesses read as fabrication in the eval. | Medium
Decide: mask PII before sending to the AI provider, or only before logging | Anthony / Sky | Changes Gate A in ADR-005a - if masked before sending, DeepSeek's data-residency disqualification is worth revisiting. | Medium
Hand over the 30 real, name-masked guest messages | Eloa | This is the actual bake-off dataset - everything built so far is a rehearsal waiting on it. | High - the whole point of ADR-005b

## Summary
Status Summary
Status | Count
Done
Blocked
Total logged today
Open blockers (Open Items sheet)